## 2024-2027
#VALUE!
| OCTOBER - 24 | NOVEMBER - 24 | DECEMBER - 24 | JANUARY - 25 | FEBRUARY - 25 | MARCH - 25 | APRIL - 25 | MAY - 25 | JUNE - 25 | JULY - 25 | AUGUST - 25 | SEPTEMBER - 25 | OCTOBER - 25 | NOVEMBER - 25 | DECEMBER - 25 | JANUARY - 26 | FEBRUARY - 26 | MARCH - 26 | APRIL - 26 | MAY - 26 | JUNE - 26 | JULY - 26 | AUGUST - 26 | SEPTEMBER - 26 | OCTOBER - 26 | NOVEMBER - 26 | DECEMBER - 26 | JANUARY - 27 | FEBRUARY - 27 | MARCH - 27 | APRIL - 27 | MAY - 27 | JUNE - 27 | JULY - 27 | AUGUST - 27 | SEPTEMBER - 27
ACTIONS
31 ACT. Opening of an e-mail box/contact form for questions about the HRS4R (in Spanish and English).
a) Entrust the design of a functional and attractive suggestion box to IT services.
b) Link the suggestion box to the emails of all HRS4R Permanent Committee members.
c) Make the suggestion box available to the entire university community.
d) Inform the entire university community of the existence of this suggestion box through the Communication Service
32 ACT.- Create a Research Career Development Advisory Unit at the Doctoral School.
a) Training of doctoral school staff in research careers with the voluntary participation of doctoral program mentors.
b) The staff of the Doctoral School will dedicate part of their day to answer questions about the career development of researchers (In-person 2 days a week for at least 2 hours).
c) Create a specific email to resolve questions about research career
d) To enable researchers, especially R1 and R2, to work on their career options in advance, inside and outside academia.
33 ACT.- Implementation of a UMH Healthy Campus Plan to optimize work performance and healthy habits among university staff.
a) To develop a UMH Healthy Campus Plan, distinguishing specific actions and/or indicators for research staff.
b) Inclusion of a research staff representative in the Commission for Health Promotion.
c) Conduct a survey for the research staff about specific health and risk management demands.
d) Implementation of the Healthy Pause for the research staff.
34 ACT. Establish research calls for emerging groups and early career researchers.
a) Budgetary approval of an extraordinary significant financial endowment for calls of emerging groups and early career researchers.
b) Mobility Calls to acquire the International PhD mention in the Doctor´s title from the Miguel Hernandez University of Elche
c) Publication of several specific calls for this action.
d) Resolution of the calls.
35 ACT. Implement a system of rewards for the most sustainable researchers through the creation of a Responsibility Index in University Research (IRIU), aligned with the principles of University Social Responsibility
a) Implement an online form for the evaluation social responsibility in research at the UMH.
b) Create a new Index in University Research (IRIU).
c) Study what type of rewards can be given to the researchers taking into consideration the IRIU result.
d) Approve the necessary procedures to achieve an efficient evaluation in a reasonable response time to requests.
e) Communication actions to present IRIU to the UMH community
36 ACT. Update the UMH Equality Plan.
a) Follow up of the UMH Gender Equality Plan which will be in force until 2026.
b) Together with the equality unit, the necessary data from the equality plan will be collected and integrated into the HRS4R action plan.
c) Participation in the discussions of the III UMH Gender Equality Plan to encompass it to the HRS4R actions.
37 ACT. Increase the proportion of full-time positions and those who hold doctorates.
a) Analysis of the characteristics of the research and teaching staff at the UMH.
b) Analysis of the number of retirements and terminations for the next years.
c) Long and medium term staff renewal plan.
d) Renewal or improvement of the public employment offer for research teaching staff each year.
e) Approval of the offer of research and teaching positions by the government council
38 ACT. Promote dissemination and exploitation of research results.
a) Internal promotion among researchers of the website ‘INGENIUM’, which contains UMH knowledge and technology offer.
b) Launch of the TRANSFIERE call for proposals to promote the participation of research staff in knowledge transfer activities (conferences, professional seminars in cooperation with the private sector, etc.).
c) Assistance and advice to increase the Technological Readiness Level (TRL) at UMH research groups (e.g. INOPROPEL Programme)
d) Assistance and advice for the creation of spin-offs (e.g. MARATHON Programme).
e) Promote among the researchers the activities and services of the UMH Communication Service
39 ACT. Redesigning of the training offer for PhD students at the UMH. Better coordination courses, a wide offer and a commitment to online training.
a) Communicate the training offer of cross-cutting courses to the Coordinators of Doctoral Programs
b) Request and review new proposals for cross-cutting training courses from the Academic Committees
c) Broaden the training offer to include at least one cross-cutting course delivered in English
d) Attain consensus on the cross-cutting training offer and submit it to the UMH Doctoral School EDUMH Steering Committee for formal approval
e) Implement the approved transversal skills courses encompassing various topics such as databases, statistics, gender perspectives in research, results dissemination, entrepreneurship, research ethics, among others.
40 ACT. Strengthen training actions on equality.
a) Entrust the Equality Unit with the programming of specific training actions for each academic year.
b) Make a schedule of activities for each academic year
c) Delivery of courses and workshops by specialized personnel.
41 ACT. Strengthen training actions on diversity.
a) Entrust the Diversity Unit with the programming of specific training actions for each academic year.
b) Entrust the Disability Care Unit with the programming of training and awareness raising actions aimed at research staff
b) Make a schedule of activities for each academic year
c) Delivery of courses and workshops by specialized personnel.
42 ACT. To organize conferences to explore international project research (R1 and R2)
a) To prepare and publish the planning of conferences.
b) To hold the conferences for researchers R1 and R2.
c) Conduct a satisfaction survey at the end of the conferences.
43 ACT. Create a training leadership program for R3 and R4.
a) Advanced training plan in EU calls, Technical and financial management of EU funded projects.
b) To communicate the specific services for these projects implemented at UMH to the R3 and R4
c) Conduct a satisfaction survey after each training.
44 ACT. Review and update the UMH academic-research career document and adapt it to the new Spanish University Law (LOSU).
a) Review reports and regulations of European and new Spanish University Law (LOSU).
b) Drafting of an academic research career document.
c) Participation of all members of the Research Commission in the revision of the draft: suggestions for improvement.
d) Participation of worker representatives in the draft revision: suggestions for improvement.
e) Presenting the report to the Executive Committee for approval
Executive Commeettee meetings
Permanent Committee meetings
Work Committee meetings