|  |  |  |
| --- | --- | --- |
| **Person responsible:**  Vice-Rector of Research | **Start date:**  September 2021 | **Linked to Action:**  22ACT: CREATE A DOCTORAL SCHOOL |

|  |
| --- |
| **Way of obtaining data:**  Survey |

|  |  |
| --- | --- |
| **Units it is measures in:**  Percentage | **Data collection periodicity:**  Annual |

|  |  |  |  |
| --- | --- | --- | --- |
| **FOLLOW-UP DATE** | **NO. PLANNED** | **NO. OBTAINED** | **COMMENTS, SUGGESTED IMPROVEMENTS** |
| December 2022 | >50% | 59% | Satisfaction is not complete for reasons beyond the control of the UMH. The assignment of 13 doctoral programs to the Doctoral School is pending in the absence of authorization from ANECA (Spanish Agency for Quality Assessment). The process has been pending for months. |
| December 2023 | >60% | 67, 3% | Response rate: 52,9% |
| December 2024 | >70% | 71,4% | Response rate: 35,2% |