|  |  |  |
| --- | --- | --- |
| **Person responsible:**  Vice-Rector of Research | **Start date:**  January 2022 | **Linked to Action:**  28ACT: IMPLEMENT A SYSTEM FOR ASSESSMENT THE IMPACT OF EACH RESEARCH PROJECT ON THE SUSTAINABLE DEVELOPMENT GOALS (SDGs**)** |

|  |
| --- |
| **Way of obtaining data:**  Office for Responsible Research (OIR) |

|  |  |
| --- | --- |
| **Units it is measures in:**  Number | **Data collection periodicity:**  Annual |

|  |  |  |  |
| --- | --- | --- | --- |
| **FOLLOW-UP DATE** | **NO. PLANNED** | **NO. OBTAINED** | **COMMENTS, SUGGESTED IMPROVEMENTS** |
| September 2023 | 148 | 135 | We had a delay implementing the SGDs impact assessment system. Data is from November 14, 2022 to July 25, 2023. Our objective was to **assess all funded research activities** (148). However, there were 13 requests that were funded but that were not research projects, like technical advice activities, so this assessment did not apply to these activities (13).  The impact of every project can be seen in the following link: [click here](https://oir-rri.shinyapps.io/repositorio_proyectos_autorizados/) |
| September 2024 | 262 | 247 | From all research activities that submit to a competitive call for funding (262), there were 15 request that were not research project, like technical advice activities, so assessment on SDGs did not apply to these activities. |
| September 2025 |  |  |  |