|  |  |  |
| --- | --- | --- |
| **Party in Charge:**Head of the Department of Communication | **Start Date:**March 2020 | **Associated to Action:**ACT 5 Have a science dissemination plan |

|  |
| --- |
| **Way of Obtaining the Data:**Registry of attendees |

|  |  |
| --- | --- |
| **Unit of Measure:**Percentage  | **Data Collection Frequency:**Numerical  |

|  |  |  |  |
| --- | --- | --- | --- |
| **MONITORING DATE** | **No. EXPECTED** | **No.** **OBTAINED** | **COMMENTS, PROPOSALS FOR IMPROVEMENT** |
| March 2020 | - | - | No data |
| October 2020 | - | - | No data |
| April 2021 | 25% | 48.6 % | The science dissemination plan was approved by the Governing Board in March 2021. However, different conferences were performed before it was approved.A total 39% of researchers polled say they have attended between 1 and 5 science dissemination conferences at the UMH. |
| September 2021 | 15% | 13.5% | Activities of the Dissemination Plan are included in the monthly science message sent to all the research staff and the teaching and research staff. |
| March 2022 | 25% | 20.1% | We created the Micro Abierto UMH (UMH Open Mic) platform to centralise the recruitment of research staff and teaching and research staff that wish to take part in dissemination talks for the general public. |
| September 2022 | 15% | 17% | We proposed and executed a course with external scientific journalists (the Superpoderes de Maldita Ciencia programme) |
| April 2023 | 25% | 22.6% | The internal training of teaching and research staff on the topic of scientific dissemination was expanded (4 courses offered in 2023) |
| October 2023  | 15% | 12.3% | We proposed a programme to increase the visibility of the role of the UMH’s female researchers on Wikipedia. |
| April 2024 | 25% | 23% | We coordinated and/or gave support to three science dissemination projects with a focus on inclusiveness and accessibility: BEATRICS, Latidos de Gea, and Academia Infancia Sana. |
| October 2024 | 15% | 13.4% | The internal training of teaching and research staff on the topic of scientific dissemination was expanded (6 courses offered in 2024). |